## Do this first
The first week, in order
Today, before anything else
1 | Start company registration | External and slow. Everything downstream waits on it, including Razorpay. Nothing about it is engineering — start it and forget it.
2 | Start Razorpay KYC | Takes longer than the integration it unblocks. Begin the moment the entity exists.
Then, ~3 days of engineering — close the holes before anything is public
3 | Remove the fail-open auth default | CommonSecurityConfig defaults bmp.security.public-paths to /**. Delete the default so a service that forgets FAILS TO START. One line; retires the bug class.
4 | Set public-paths in the 4 services missing it | bmp-salon, bmp-payment, bmp-review, bmp-notification. Until this lands, step 3 stops them booting — do both together.
5 | Audit bmp-salon's 35 unprotected endpoints | The real work, not the config. Each one: genuinely public, or needs @PreAuthorize? 51 endpoints, only 16 protected today.
6 | Add a guard so this cannot recur | A tiny test or build check asserting every service sets public-paths. Cheaper than remembering.
7 | Fix the three wrong comments and the RUN_LOCALLY table | They claim the principal is always null under /**. It isn't — JwtAuthFilter always runs. Someone will misdiagnose the next one.
Same week, free
8 | Stop running config-server and monitoring | Both are optional: imports; services boot without them. 13 processes to 11, today, for nothing.
9 | Write the no-new-services rule into CONTEXT.md | Whatever comes next goes in an existing service. Rules that live only in a chat do not survive.
10 | Declare the console frozen | Feature-complete for a team of zero. Say so in BMP-ADMIN/CONTEXT.md so nobody 'finishes' it.
After that
11 | Agree commission with 3 real salon owners | Then start signing salons. This is the long pole — 20+ days — so it runs in the background from here on.
12 | Begin Razorpay integration (Track 1) | Once KYC clears. 13 days to a booking that can actually complete.
Why the security work comes before the deployment work
52 endpoints across four services currently need no credential at all. Today that is harmless — nothing is deployed, so nothing is reachable. Track 2 puts it on a public VM, and at that moment it stops being harmless.
So the dependency is hard: steps 3-6 must land before D2. It is ~3 days now, or an incident later.

## Open endpoints
Measured, not asserted — where authentication is missing today
Service | public-paths | Endpoints | With @PreAuthorize | Reachable with NO token
bmp-salon | ABSENT | 51 | 16 | 35
bmp-notification | ABSENT | 7 | 0 | 7
bmp-review | ABSENT | 6 | 0 | 6
bmp-payment | ABSENT | 4 | 0 | 4
bmp-booking | set | 19 | 9 | 0
bmp-rewards | set | 15 | 6 | 0
bmp-user | set | 13 | 13 | 0
TOTAL |  | 115 | 44 | 52
The cause, in one line
CommonSecurityConfig: @Value("${bmp.security.public-paths:/**}"). A service that never mentions the property gets permitAll() on everything. Omission fails open.
Why this is an architecture point, not a config bug
In one process, "is this authenticated?" is decided once. Thirteen services turned it into thirteen decisions, and four are still wrong. Distribution did not cause a bug — it caused a bug class, and multiplied the places it can hide.
A correction worth reading
Comments in bmp-booking and bmp-rewards claim that under /** the principal was always null, so @PreAuthorize could not run. That is wrong. JwtAuthFilter runs on every request and populates the SecurityContext whenever a valid token is present; permitAll() governs the authorization decision, not filter execution. The real hole is narrower and still serious: anything WITHOUT @PreAuthorize needs no token. Left uncorrected, someone misdiagnoses the next occurrence.
Exposure today
Zero — nothing is deployed. That changes the day Track 2 lands, which is why the fix is sequenced before it.

## Plan
Full sequenced plan — Track 0 runs in parallel from day one
# | Track | ID | Task | Why it matters | Type | Est. days | Depends on | Owner | Status
1 | Track 0 — Company & supply (not code) | S1 | Register the company | Fills [[REGISTERED_ENTITY_NAME]] in Privacy/Terms; gates Razorpay KYC; nobody wires money to a person. | External | 5 | — |  | To Do
2 | Track 0 — Company & supply (not code) | S2 | Razorpay account + KYC | Start day one. Takes longer than the integration. All of Track 1 waits on live keys. | External | 7 | S1 |  | To Do
3 | Track 0 — Company & supply (not code) | S3 | Agree commission % with 3 real owners | Every booking freezes a commission basis no salon has agreed to. Find out before it is in a deck. | Business | 3 | — |  | To Do
4 | Track 0 — Company & supply (not code) | S4 | Sign 10 salons in one neighbourhood | THE bottleneck. Indiranagar — the seed data already assumes it. Ten live salons beats the whole backlog. | Business | 20 | S3 |  | To Do
5 | Track 0 — Company & supply (not code) | S5 | Load their real services and prices | Replaces seed data with a real catalogue. Cheap, and the demo stops looking like a demo. | Ops | 2 | S4 |  | To Do
6 | Track H — Close the holes, stop the bleeding | H1 | Remove the fail-open auth default | Delete the :/** default in CommonSecurityConfig so a service that forgets fails to START, not to authenticate. Highest value change in the codebase. | Backend | 0.5 | — |  | To Do
7 | Track H — Close the holes, stop the bleeding | H2 | Set public-paths in the 4 missing services | bmp-salon, payment, review, notification. Must ship WITH H1 or those services stop booting. | Backend | 0.5 | H1 |  | To Do
8 | Track H — Close the holes, stop the bleeding | H3 | Audit bmp-salon's 35 unprotected endpoints | The actual work. Per endpoint: genuinely public, or needs @PreAuthorize? 51 endpoints, 16 protected. | Backend | 1 | H2 |  | To Do
9 | Track H — Close the holes, stop the bleeding | H4 | Guard so it cannot recur | A test asserting every service sets public-paths. Cheaper and more reliable than remembering. | Backend | 0.25 | H3 |  | To Do
10 | Track H — Close the holes, stop the bleeding | H5 | Correct the wrong comments + docs | bmp-booking/bmp-rewards comments and RUN_LOCALLY §8 misstate the failure mode. Wrong docs cause wrong diagnoses. | Docs | 0.25 | H3 |  | To Do
11 | Track H — Close the holes, stop the bleeding | H6 | Stop running config-server + monitoring | Already optional: imports. 13 processes to 11 for free. Update RUN_LOCALLY's default list. | DevOps | 0.25 | — |  | To Do
12 | Track H — Close the holes, stop the bleeding | H7 | Write the no-new-services rule into CONTEXT.md | Next thing goes in an existing service. A rule that lives only in chat does not survive the week. | Docs | 0.1 | — |  | To Do
13 | Track H — Close the holes, stop the bleeding | H8 | Declare the console frozen | Feature-complete for a team of zero. Say so in BMP-ADMIN/CONTEXT.md so nobody 'finishes' it. | Docs | 0.1 | — |  | To Do
14 | Track 1 — Make one rupee move | P1 | Razorpay test keys wired locally | Keys go in local-secrets.ps1 (gitignored). Never a migration, never application.yml. | Backend | 0.5 | S2 |  | To Do
15 | Track 1 — Make one rupee move | P2 | bmp-payment: create order on booking | First half of the loop — booking returns an order id the client can pay against. | Backend | 2 | P1 |  | To Do
16 | Track 1 — Make one rupee move | P3 | Webhook + signature verification | Verify before trusting. An unverified webhook lets anyone mark any booking paid. | Backend | 2 | P2 |  | To Do
17 | Track 1 — Make one rupee move | P4 | PENDING to CONFIRMED, idempotently | Razorpay retries. Handle the same event twice without double-confirming or double-counting GMV. | Backend | 2 | P3 |  | To Do
18 | Track 1 — Make one rupee move | P5 | Failure, timeout and abandonment | Most of real traffic. An abandoned payment must release the held slot or availability silently rots. | Backend | 2 | P4 |  | To Do
19 | Track 1 — Make one rupee move | P6 | Manager check-in | Built already, unreachable because no booking leaves PENDING. Near-free once P4 lands. | Backend | 1 | P4 |  | To Do
20 | Track 1 — Make one rupee move | P7 | Tests on the money path only | Not coverage. Booking creation, coupon redemption, webhook idempotency — where a silent bug costs cash. | Backend | 3 | P4 |  | To Do
21 | Track 1 — Make one rupee move | P8 | Settle salons by hand | A deliberate non-build. An hour a week at 10 salons vs a week building Route. Revisit at ~50. | Decision | 0.5 | S4 |  | To Do
22 | Track 2 — Make it clickable | D1 | Dockerfiles for the 5 core services | None exist. Gateway, auth, user, salon, booking — not all 13. | DevOps | 2 | — |  | To Do
23 | Track 2 — Make it clickable | D2 | One VM: compose + nginx + TLS | Your own compose comment prices the pilot at Rs 3-6k/month. BLOCKED ON TRACK H — do not expose 52 open endpoints. | DevOps | 2 | D1, H3 |  | To Do
24 | Track 2 — Make it clickable | D3 | Deploy the web app | EXPO_PUBLIC_USE_MOCKS=false, pointed at the deployed gateway. | Frontend | 1 | D2 |  | To Do
25 | Track 2 — Make it clickable | D4 | Turn every dev bypass off | BMP_DEV_MASTER_OTP empty, both USE_MOCKS false, BMP_ADMIN_DEV_STAFF unset. Three flags separate a demo from a product. | DevOps | 0.5 | D3 |  | To Do
26 | Track 2 — Make it clickable | D5 | Smoke-test runbook | Ten minutes, written down, after every deploy. You will demo this live and unrehearsed at least once. | DevOps | 0.5 | D4 |  | To Do
27 | Track 3 — Be able to answer questions | N1 | Events table + write on key actions | Signup, search, booking created, confirmed, cancelled. A table and an insert — not a vendor. | Backend | 2 | P4 |  | To Do
28 | Track 3 — Be able to answer questions | N2 | Weekly numbers query | You cannot currently answer 'how many bookings last week?'. Every investor asks. | Backend | 1 | N1 |  | To Do
Effort by track
| Track 0 — Company & supply (not code) |  |  |  |  | 37 | 0 / 5
| Track H — Close the holes, stop the bleeding |  |  |  |  | 2.95 | 0 / 8
| Track 1 — Make one rupee move |  |  |  |  | 13 | 0 / 8
| Track 2 — Make it clickable |  |  |  |  | 6 | 0 / 5
| Track 3 — Be able to answer questions |  |  |  |  | 3 | 0 / 2
| TOTAL |  |  |  |  | 61.95 | 0 / 28
| Engineering days only (Tracks H, 1, 2, 3): |  |  |  |  | 24.95
Yellow cells are yours: Owner and Status. Type Done in Status and the counters update.
Estimates are rough engineering days for ONE person — my estimate, not measured from your team's history.
Track 0 is waiting and legwork, not desk work. Do not add it to an engineering timeline.
Track H is amber because it is the only track with a hard ordering constraint: it must precede D2.

## Not now
Not now — and why. Adding to this list is progress.
Thing | Status today | Why it waits
Rewriting into a monolith | 13 services | The cost is sunk and the code works. A rewrite is a month of zero customer value. Consolidate opportunistically, when a service needs real work anyway — not before.
Any NEW service | 13 already | Past the point where another adds capability. It adds a deploy target, a failure mode, and one more place to forget public-paths.
Razorpay Route (auto split) | Not started | An hour a week by hand at 10 salons vs a week of work plus its own KYC. Revisit at ~50.
Deploying the staff console | Local, on mocks | No support team. Deploying adds an internet-facing admin surface that reads every customer's phone number, for zero benefit.
More console features | Feature-complete | CSV export, pagination, canned responses, QR for 2FA — all for a team that does not exist. Frozen (see H8).
Reviews UI | Backend exists | Needs completed bookings. Meaningless before payments, near-free after.
Owner dashboard | Not started | Owners ask at ~20 salons. Before that you are the dashboard — call them.
Reschedule | Not started | Cancel-and-rebook covers this volume. Real reschedule touches slot locking and refunds.
SMS / WhatsApp OTP | Stubbed to logs | India DLT registration is weeks of paperwork. Email OTP works today and costs nothing.
Kafka / Cloud Bus tuning | Working | Fine at zero load. Tuning a system with no traffic.
DPDP erasure that truly anonymises | Deactivates only | A real obligation, triggered by a request you have not received. Track it; do not build it this month.
Test coverage beyond the money path | Zero tests | Broad coverage on pre-PMF code you may delete is waste. The money path is the exception.

## Numbers to hit
What you want to be able to say in a meeting
Fill the yellow column as you go. These are the questions asked in almost every first meeting for a marketplace — not targets I am setting for you.
Metric | Today | Where it comes from | Notes
Live salons | 0 | Count them yourself | The number that matters most right now. Zero today.
Bookings completed | 0 | Track 3 / N2 | Completed, not created. A PENDING booking is not a booking.
GMV (Rs) | 0 | Track 3 / N2 | Stored as integer paise — divide by 100 before quoting it.
Take rate (%) | 0 | Commission on confirmed | Frozen per booking in code. Confirm a real salon agreed to it (S3).
Repeat rate (%) | 0 | Track 3 / N2 | Customers with 2+ completed bookings. Separates a marketplace from a directory.
Cancellation rate (%) | 0 | Track 3 / N2 | High cancellations read as a supply-quality problem. Know it before you are asked.
Honest reading of today:
No live salons and no completed bookings. Every number above is zero, and no amount of code changes that. Track 0 first.